## Introduction
Climate Risk and Opportunity Assessment workbook for regeneration and built environment projects
v1
This workbook has been developed by Sniffer and Adaptation Scotland as part of the Climate Ready Clyde Accelerator programme. It is designed to support partners to assess the resilience of projects to current climate and future climate change.
The tool is comprised of the following elements:
Step 1. Define the project and Scope: Broad background information about your project and the relevant items in scope of the assessment
Step 2: Vulnerability Assessment - To assess how sensitive the project is to a range of climate variables
Step 3: Hazard and Exposure Assessment - To assess the exposure of the project to current and future climate change
Sep 4: Potential climate-related impacts - A module to view the overall vulnerability of the project, based on the outputs of module 2 and module 3
Step 5: Risk Register - A template to assess the key risks to your project arising from the vulnerabilities identified
The toolkit is based on the EU non-paper guidelines for project managers on making vulnerable investments climate resilient (available here: http://climate-adapt.eea.europa.eu/metadata/guidances/non-paper-guidelines-for-project-managers-making-vulnerable-investments-climate-resilient ).
All contents of this workbook © Sniffer, 2019, and may not be reproduced or modified without permission.
Sniffer is grateful to East Dunbartonshire Council, University of Strathclyde, Stirling Council and the Scottish Cities Allliance for their support in development of this tool.
Development of the tool has been funded by Scottish Government.

## 1. Scope
Step 1 - Define the scope of the assessment
This section should be used to enter basic information about your project to support the assessment process.
| Project Name: | Sample project |  | Project Type: | [Enter the type of project]
| Overall project budget | [How much will be spent] |  | Partners: | [List key partners involved in delivery]
| Project description |  | [Enter a short summary descripion of the project]
| Estimated completion date |  |  |  |  | Assesment Horizon | 2050s (2040 - 2069) | The time period used for assessing climate change resilience
| Project lifetime |  |  |  | Enter the approximate number of years the project will be in existence once completed
| Project Scope | Outline the key features in scope of each category of the risk assessment
On-site assests and processes
Inputs
Outputs
Transport Links
Contact Details
| Project Manager |  |  | Climate Resilience Assessor
| Telephone No |  |  | Telephone No.
| Email |  |  | Email
Associated evidence which supports the assessment
The following evidence has been used to support your assumptions in the development and delivery of the project
[List the relevant documents that exist to date - e.g. Flood Risk Assessment, Sustainability Assesment/Appraisal]

## 2. Vulnerability
Step 2: Vulnerability Assessment
Project Name | Sample project | [9 empty] | Project Type:
Project scope | Incremental Air Temperature increase | Extreme temperature/ heatwave | Incremental rainfall change | Extreme rainfall change | Average wind speed | Maximum wind speed | Humidity | Solar radiation | Relative Sea Level Rise | Seawater Temperature | Water Availability | Storms | Flooding (coastal and fluvial) | Ocean PH | Dust storms | Coastal erosion | Soil Erosion | Soil Salinity | Air Quality | Ground instability / landslides | Urban Heat Island | Growing season
On-site assets and processes | H | H | L | M | [6 empty] | H
Inputs | M | M | M | M | [6 empty] | M
Outputs | H | L | L | L | [6 empty] | L
IT and Transport links | H | M | L | M | [6 empty] | L
Average | 3 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Summary of vulnerability
Describe the key elements of the project scope that are vulnerable? Are there particular elements that are exposed to multiple
Assumptions and Evidence
Areas for further investigation
Note on A6: Note: The physical assets on the site itself, as well activities undertaken on the site (e.g care provision, teaching)
Note on A7: Note: The materials, and resources that will be used by the site in its functioning (e.g. energy, water, but also supplies and services)
Note on A8: Guidance note: Products produced, outcomes or revenue
Note on A9: Note: The way in which users access the site (private transport, bus, rail, cycling, air)

## 3. Exposure
Step 2. Exposure Assessment
2a. Exposure to current climate
Primary climate hazard/secondary effects | Rating | Data sources used for assessment / additional notes
Incremental Air Temperature increase | M
Extreme temperature increase | H | Local Climate Impacts Profile
Incremental rainfall change | L
Extreme rainfall change | L
Average wind speed | M
Maximum wind speed | M
Humidity | H
Solar radiation | L
Water Availability | M
Storms | L
Flooding (coastal and fluvial) | L
Dust storms | L
Air Quality | L
Urban Heat Island | M
2b. Exposure to future climate | Period covered: | 2050s (2040 - 2069)
Primary climate hazard/secondary effects | Rating | Data sources used for assessment / additional notes
Incremental Air Temperature increase | H
Extreme temperature increase | H | UKCP18, assessment of future heatwaves by University of Edinburgh
Incremental rainfall change | M
Extreme rainfall change | M
Average wind speed | H | UKCP18
Maximum wind speed | H | UKCP18
Humidity
Solar radiation
Water Availability
Storms
Flooding (coastal and fluvial)
Dust storms
Air Quality
Urban Heat Island
Definition of exposure standards
Decide what comprises high, medium and low ratings for exposure, if not already identified in the datasets
This should include past records, experience of impacts on similar projects, ritical thresholds from design standards
Safety margins/tolerances
High exposure
Medium exposure
Low exposure

## 4. Risk likelihood
Step 4. Review risk likelihood
[13 empty] | Project Name | Sample project
|  | 3a - Risk likelihood to Current Climate | [6 empty] | 3b Risk likelihoods for Future Climate |  |  |  | Time Period: | 2050s (2040 - 2069)
|  | High |  | Incremental Air Temperature increase |  |  |  |  | High |  |  |  |  | Incremental Air Temperature increase
| Vulnerability | Medium | Extreme rainfall change | Water Availability |  |  |  | Vulnerability | Medium |  | Extreme rainfall change
|  | Low | Incremental rainfall change | [5 empty] | Low |  | Incremental rainfall change
|  |  | Low | Medium |  |  | High |  |  | Low | Medium |  |  | High
[5 empty] | Exposure | [6 empty] | Exposure
Relevant notes / commentary
[5 empty] | Vulnerability | Exposure | [5 empty] | Vulnerability | Exposure
|  | Incremental Air Temperature increase |  |  | H | M | [5 empty] | H | H
|  | Extreme temperature/ heatwave |  |  | M | N/A | [5 empty] | M | N/A
|  | Incremental rainfall change |  |  | L | L | [5 empty] | L | M
|  | Extreme rainfall change |  |  | M | L | [5 empty] | M | M
|  | Average wind speed |  |  | N/A | M | [5 empty] | N/A | H
|  | Maximum wind speed |  |  | N/A | M | [5 empty] | N/A | H
|  | Humidity |  |  | N/A | H | [5 empty] | N/A | N/A
|  | Solar radiation |  |  | N/A | L | [5 empty] | N/A | N/A
|  | Relative Sea Level Rise |  |  | N/A | N/A | [5 empty] | N/A | N/A
|  | Seawater Temperature |  |  | N/A | N/A | [5 empty] | N/A | N/A
|  | Water Availability |  |  | M | M | [5 empty] | M | N/A
|  | Storms |  |  | N/A | L | [5 empty] | N/A | N/A
|  | Flooding (coastal and fluvial) |  |  | N/A | L | [5 empty] | N/A | N/A
|  | Ocean PH |  |  | N/A | N/A | [5 empty] | N/A | N/A
|  | Dust storms |  |  | N/A | L | [5 empty] | N/A | N/A
|  | Coastal erosion |  |  | N/A | N/A | [5 empty] | N/A | N/A
|  | Soil Erosion |  |  | N/A | N/A | [5 empty] | N/A | N/A
|  | Soil Salinity |  |  | N/A | N/A | [5 empty] | N/A | N/A
|  | Air Quality |  |  | N/A | L | [5 empty] | N/A | N/A
|  | Ground instability / landslides |  |  | N/A | N/A | [5 empty] | N/A | N/A
|  | Urban Heat Island |  |  | N/A | M | [5 empty] | N/A | N/A
|  | Growing season |  |  | N/A | N/A | [5 empty] | N/A | N/A

## 5. Risk Register
Step 5: Define and score risks
Project: | Sample project |  | Last reviewed:
Completed by:
Completed on:
CURRENT CLIMATE RISK REGISTER | [10 empty] | FUTURE CLIMATE CHANGE RISK REGISTER
|  | 2019 |  |  |  | 2019 | [5 empty] | 2050s (2040 - 2069) |  |  | M's & C's | 2050s (2040 - 2069) |  |  | Filling the 'Adaptation Gap'
Risk Description | Consequence | Inherent Risk |  |  | Mitigants & Controls (Exisiting) | Residual Risk |  |  | Treatments (Proposed) | Risk Owner | Climate Change Risk Modifier | Inherent Risk |  |  |  | Residual Risk |  |  | Actions your organisation could take now (2019) and in future to strengthen existing mitigants and controls and, introduce new ones to reduce residual risk
|  | Likelihood | Impact | Risk Rating |  | Likelihood | Impact | Risk Rating |  |  |  | Likelihood | Impact | Risk Rating |  | Likelihood | Impact | Risk Rating | Actions that could be taken now (2019) | Actions that may need to be taken in the future
Hazard and impact (on the objective) | More detail on the consequences | [9 empty] | How will climate change modify the risk? |  |  |  | Assume same mitigants and controls as identified for 2014
Roads and footpaths closed due to coastal flooding and erosion | Impact on public safety; fewer tourists to visiting areas; damage to path network needing repair; damage to reputation; etc. | 3 | 3 | 9 | Inspection regimes and good housekeeping measures in place and working effectively; Emergency surface water and river flood procedures in place and have proven effective. Shoreline Management Plan has been produced; The Severe Weather Response Plan has been developed over the past few years and ensures a co-ordinated and consistent multi-agency response across the county; Flooding advice is given on the Council website and directs people to the relevant pages on the SEPA website; Flooding and drainage issues are considered when processing planning applications; | 3 | 2 | 6 | The Council is working with other agencies to enhance community resilience. |  | Sea level rise will increase likelihood of flooding and rates of coastal erosion | 4 | 4 | 16 |  | 4 | 3 | 12 | Coastal change assesment and updating of shoreline management plans. | Managing and planning for coastal change. Protecting or moving roads and footpaths.
Damage to roads, property, harbours and natural heritage sites due to coastal flooding and erosion | Impact on public safety; damage needing repair; increase in claims against the Council; etc.

## Dropdown Options or List (hidden)
Tool Configuration
Project Scope
Exposure Assessment |  |  | Sensitivity Assessment |  |  | Landscaping | Buildings |  | Energy |  | Climatic Variables
Select rating | [10 empty] | (Select variable)
Incremental Air Temperature increase
H |  |  | H |  |  | Yes |  |  | Yes |  | Extreme temperature increase
M |  |  | M |  |  | No | No |  | No |  | Incremental rainfall change
L |  |  | L |  |  |  | Domestic |  |  |  | Extreme rainfall change
[7 empty] | Non-Domestic |  |  |  | Average wind speed
ExposureList2' |  |  | SA' |  |  |  | Mixed - Primarily Domestic |  |  |  | Maximum wind speed
[7 empty] | Mixed - Primarily Non-Domestic |  |  |  | Humidity
Solar radiation
Time Periods | [10 empty] | Relative Sea Level Rise
Select a time period | [5 empty] | Project Type |  |  |  |  | Seawater Temperature
2020s (2010-2039) | [10 empty] | Water Availability
2030s (2020-2049) | [5 empty] | Domestic Building(s) |  |  |  |  | Storms
2040s (2030 - 2059) | [5 empty] | Energy |  |  |  |  | Flooding (coastal and fluvial)
2050s (2040 - 2069) | [5 empty] | Mixed use development |  |  |  |  | Ocean PH
2060s (2050 - 2079) | [5 empty] | Non domestic building(s) |  |  |  |  | Dust storms
2070s (2060 - 2089) | [5 empty] | Non domestic building(s) - Care Home |  |  |  |  | Coastal erosion
2080s (2070 - 2099) | [10 empty] | Soil Erosion
TimPer' | [10 empty] | Soil Salinity
Air Quality
Ground instability / landslides
Risk Matrix | [10 empty] | Urban Heat Island
Growing season
Consequences
|  | 1 | 2 | 3 | 4 | 5 | Consequences |  | Likelihood
| 1 | 1 | 2 | 3 | 4 | 5 | 1 | Insignificant | 1 | Rare
| 2 | 2 | 4 | 6 | 8 | 10 | 2 | Minor | 2 | Unlikely
| 3 | 3 | 6 | 9 | 12 | 15 | 3 | Moderate | 3 | Moderate
| 4 | 4 | 8 | 12 | 16 | 20 | 4 | Major | 4 | Likely
| 5 | 5 | 10 | 15 | 20 | 25 | 5 | Catastrophic | 5 | Almost certain
Likelihood